## Sheet1
Risk | Impact | Likelihood | Fallout | Mitigation | Impact After | Likelihood after
Lack of experience in weather prediction algorithms | High | Medium | The site will incorrectly predict the weather | We all need to research weather prediction algorithms and how they work/can be implemented | Medium | Low
Missing a Project meeting | Medium | Medium | If someone misses the meeting, they will not be up to date with progress, the next tasks and deadlines | Minutes of each meeting will be recorded. All tasks will be updated on Jira with due dates, and assignees | Low | Low
Programming Issues | High | Low | Incorrect algorithms/ Broken GUI | Extensive testing throughout development | Medium | Low